## Route Plan
City | State | Estimated Arrival | Miles from Start | Days (with rest) | Week Number | Population | Significance | Avg Hi Temp (°F) | Avg Lo Temp (°F) | Latitude | Longitude | major
Key West | FL | 2026-02-27 | 12.3 | 0.3 | 1 | 26000 | Starting point - Southernmost point in continental US | 73 | 58 | 24.5551 | -81.78 | Y
Miami | FL | 2026-03-02 | 181.1 | 3.9 | 1 | 449514 | Major metropolitan area, cultural hub | 79 | 64 | 25.7617 | -80.1918 | Y
Fort Lauderdale | FL | 2026-03-04 | 259.4 | 5.6 | 1 | 182760 | Beach city, Venice of America | 78 | 63 | 26.1224 | -80.1373 | Y
West Palm Beach | FL | 2026-03-05 | 296.2 | 6.4 | 1 | 117415 | Coastal resort city | 77 | 62 | 26.7153 | -80.0534 | Y
Vero Beach | FL | 2026-03-07 | 400.6 | 8.6 | 2 | 17163 | Quiet coastal town | 76 | 61 | 27.6386 | -80.3973
Melbourne | FL | 2026-03-07 | 405.2 | 8.7 | 2 | 84678 | Space Coast city | 75 | 60 | 28.0836 | -80.6081
Titusville | FL | 2026-03-08 | 422 | 9.1 | 2 | 48789 | Gateway to Kennedy Space Center | 75 | 60 | 28.6122 | -80.8075
Daytona Beach | FL | 2026-03-08 | 455.8 | 9.8 | 2 | 72647 | Famous beach and NASCAR | 74 | 59 | 29.2108 | -81.0228
Saint Augustine | FL | 2026-03-10 | 501.8 | 10.8 | 2 | 14329 | Oldest continuously inhabited European settlement in US | 73 | 58 | 29.9012 | -81.3124 | Y
Tallahassee | FL | 2026-03-12 | 658.4 | 14.2 | 3 | 196169 | Florida state capital | 72 | 57 | 30.4383 | -84.2807 | Y
Pensacola | FL | 2026-03-15 | 934.6 | 20.1 | 3 | 54312 | Historic naval aviation hub | 72 | 57 | 30.4213 | -87.2169
Biloxi | MS | 2026-03-20 | 1052.8 | 22.7 | 4 | 49449 | Casino resort town on Gulf Coast | 72 | 57 | 30.396 | -88.8853 | Y
Gulfport | MS | 2026-03-26 | 1077.3 | 23.2 | 4 | 72926 | Gulf port city | 72 | 57 | 30.3674 | -89.0928
Slidell | LA | 2026-03-27 | 1121.9 | 24.1 | 4 | 28781 | Near New Orleans | 72 | 57 | 30.2752 | -89.7812
New Orleans | LA | 2026-03-28 | 1169.4 | 25.2 | 4 | 383997 | Major cultural hub - jazz, cuisine, French Quarter | 73 | 58 | 29.9511 | -90.0715 | Y
Baton Rouge | LA | 2026-03-29 | 1326 | 28.5 | 5 | 227470 | Louisiana state capital | 72 | 57 | 30.4515 | -91.1871 | Y
Lafayette | LA | 2026-04-02 | 1388
Navasota | TX | 2026-04-08 | 1636 | 35.2 | 6 | 7786 | Small Texas town | 82 | 64 | 30.388 | -96.0877 | Y
Austin | TX | 2026-04-11 | 1867.7 | 40.2 | 6 | 961855 | Texas state capital, tech hub | 82 | 64 | 30.2672 | -97.7431 | Y
San Antonio | TX | 2026-04-12 | 1933 |  |  |  | Military City
Fredericksburg | TX | 2026-04-14 | 2057 | 42.5 | 7 | 11216 | German heritage, wine country | 82 | 64 | 30.2752 | -98.872 | Y
Van Horn | TX | 2026-04-21 | 2368.3 | 53.7 | 8 | 1930 | Small desert town | 93 | 60 | 31.0399 | -104.8308
El Paso | TX | 2026-05-01 | 2557 | 58.6 | 9 | 678815 | Border city with Mexico | 92 | 59 | 31.7619 | -106.485 | Y
Las Cruces | NM | 2026-05-06 | 2738.1 | 63.3 | 10 | 111385 | NMSU town | 101 | 65 | 32.3199 | -106.7637 | Y
Lordsburg | NM | 2026-05-11 | 2916.1 | 68 | 10 | 2797 | Small border town | 101 | 65 | 32.3503 | -108.707
Phoenix | AZ | 2026-05-20 | 3264.5 | 77.1 | 12 | 1608139 | 5th largest US city | 99 | 63 | 33.4484 | -112.074 | Y
Quartzsite | AZ | 2026-05-23 | 3379.6 | 80.1 | 12 | 3677 | Desert RV town | 99 | 63 | 33.6639 | -114.2294
Blythe | CA | 2026-05-23 | 3395 | 80.5 | 12 | 18317 | Colorado River border | 99 | 63 | 33.6103 | -114.5963
Indio | CA | 2026-05-24 | 3439.5 | 81.7 | 12 | 89137 | Coachella Valley | 87 | 66 | 33.7206 | -116.2156
Palm Springs | CA | 2026-05-25 | 3482.4 | 82.8 | 12 | 44575 | Desert resort | 87 | 66 | 33.8303 | -116.5453
San Bernardino | CA | 2026-05-28 | 3586.8 | 85.5 | 13 | 222101 | Historic Route 66 | 86 | 65 | 34.1083 | -117.2898 | Y
Fontana | CA | 2026-05-29 | 3626.7 | 86.6 | 13 | 208393 | Inland Empire industrial | 86 | 65 | 34.0922 | -117.435 | Y
Los Angeles | CA | 2026-05-31 | 3701.9 | 88.5 | 13 | 3898747 | 2nd largest US city | 86 | 65 | 34.0522 | -118.2437 | Y
Ontario | CA | 2026-06-04 | 3863 | 92.8 | 14 | 175265 | Major airport hub | 86 | 65 | 34.0633 | -117.6509 | Y
Victorville | CA | 2026-06-06 | 3913.7 | 94.1 | 14 | 134810 | High desert city | 91 | 70 | 34.5362 | -117.2928 | Y
Barstow | CA | 2026-06-06 | 3915.2 | 94.1 | 14 | 24829 | Mojave Desert hub | 90 | 69 | 34.8958 | -117.0228
Henderson | NV | 2026-06-08 | 4010.4 | 96.6 | 14 | 320189 | Las Vegas suburb | 100 | 64 | 36.0395 | -114.9817 | Y
St. George | UT | 2026-06-13 | 4203.7 | 101.7 | 15 | 95342 | Gateway to Zion | 99 | 63 | 37.0965 | -113.5684 | Y
Hurricane | UT | 2026-06-19 | 4309.6 | 107.4 | 16 | 20036 | Near Zion NP | 99 | 63 | 37.1753 | -113.2899
Kanab | UT | 2026-06-21 | 4378.7 | 109.2 | 16 | 4700 | Gateway to Grand Staircase | 99 | 63 | 37.0475 | -112.5263
Marble Canyon | AZ | 2026-06-21 | 4394 | 109.6 | 16 | 50 | Colorado River crossing | 99 | 63 | 36.8189 | -111.6378
Lee's Ferry | AZ | 2026-06-21 | 4398.7 | 109.8 | 16 | 0 | Historic river crossing | 99 | 63 | 36.8642 | -111.595 | Y
Cameron | AZ | 2026-06-24 | 4495.3 | 112.3 | 17 | 885 | Trading post near Grand Canyon | 101 | 65 | 35.8567 | -111.4178
Flagstaff | AZ | 2026-06-26 | 4562.9 | 114.1 | 17 | 76831 | Mountain town, Grand Canyon gateway | 102 | 66 | 35.1983 | -111.6513 | Y

## Trip Assumptions
CROSS-COUNTRY CYCLING TRIP - PLANNING ASSUMPTIONS
BASIC TRIP INFORMATION
Start Location | Key West, Florida
End Location | Flagstaff, Arizona
Start Date | February 27, 2026
Target End Date | June 21, 2026
Total Available Days | 114 days
Total Route Distance | 4464.4 miles (per RideWithGPS)
DAILY TRAVEL PACE
Average Daily Miles (Key West to Austin) | 55 miles/day
Average Daily Miles (Austin to Flagstaff) | 45 miles/day (due to elevation gain)
Rationale | Reduced pace after Austin accounts for increased climbing in Southwest
REST DAY SCHEDULE
Weekly Rest Days | 1 rest day per 7 days of travel
Total Weekly Rest Days | 13 days
Special Extended Rests
- Fredericksburg, TX | 3 consecutive days
- St. George, UT | 3 consecutive days
Total Special Rest Days | 6 days
Total Rest Days | 19 days
BUFFER/CONTINGENCY TIME
Purpose | Weather delays, mechanical issues, fatigue, unplanned stops
Total Buffer Days | 3.3 days
Distribution | Evenly distributed throughout trip proportional to distance
Buffer Rate | 0.0007 days per mile
TIME BREAKDOWN
Pure Travel Days | 91.7 days
Weekly Rest Days | 13 days
Special Rest Days | 6 days
Buffer/Contingency Days | 3.3 days
TOTAL | 114 days
ROUTE NOTES
Route Source | RideWithGPS Route #53807324
Route Type | Roads and bike paths
General Direction | Florida East Coast → Gulf Coast → Texas → Southwest → Utah/Arizona
Major Regions | Atlantic Coast FL, Florida Panhandle, Gulf Coast (AL/MS/LA),
East Texas, Central Texas Hill Country, West Texas Desert,
Southern New Mexico, Southern Arizona Desert, California Desert,
Nevada, Southern Utah, Northern Arizona
HIGHLIGHTED CITIES IN SPREADSHEET
Yellow | Original waypoint cities from initial planning
Green | Extended rest stop cities (3 days each)
TEMPERATURE DATA
Source | Estimated based on latitude, longitude, and arrival month
Note | Actual temperatures may vary; check forecasts closer to travel dates
IMPORTANT ASSUMPTIONS & LIMITATIONS
1. | Route distance based on RideWithGPS calculation (4,464.4 miles)
2. | Daily mileage assumes favorable conditions; adjust as needed
3. | Elevation changes after Austin require reduced daily mileage
4. | Buffer days account for: weather delays, mechanical breakdowns,
fatigue, navigation issues, and unexpected events
5. | Rest days scheduled at 1 per 7 travel days (more conservative schedule
allows additional buffer days for weather/mechanical issues)
6. | Fredericksburg and St. George selected for extended rests
(cultural interest, amenities, strategic location)
7. | City list includes intermediate stops; not all are overnight locations
8. | Arrival dates are estimates; actual progress may vary
9. | Weather in Southwest (May-June) can be extremely hot (100°F+)
10. | This is a planning document; adjust in real-time based on conditions
CONTACT & UPDATES
Note | Keep emergency contacts informed of progress
Consider posting regular updates to social media or blog
Download offline maps for areas with poor cell service
EMERGENCY PLANNING
Recommended | Carry emergency contact information
Know locations of bike shops along route
Have contingency plans for severe weather
Carry basic repair tools and spare parts
Purchase trip insurance if possible